## Introduction
Key Objectives of Weymouth Town Council to May 2025
This plan details the community investment, internal development and project work that Weymouth Town Council will carry out over the next 4 years to meet the objectives in its agreed Corporate Plan. As such it does not contain all of the ongoing work that helps us meet our day-to-day responsibilities and core functions e.g. customer service, financial management, maintenance, HR, democratic services, communications etc.
The work will be regularly reviewed at Full Council meetings and is liable to regular change as projects are completed, instigated, and adjusted. This plan will be supported by detailed Service Plans and performance management processes that will also be regularly monitored in Full Council as well as in the Council’s Committees. Full details of the reports to Council meetings can be found on our website www.weymouthtowncouncil.gov.uk. Any questions relating to this plan, which forms an annex to the Corporate Plan itself can be sent to office@weymouthtowncouncil.gov.uk where one of our team will be happy to assist you.
SMT refers to the Senior Management Team of the Council.

## A Improve wellbeing of public
A - Improve the wellbeing of the people of Weymouth
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding | Timescale | Comments | What success looks like
A 1 | Work with partners on the development of a Weymouth Wildlife Nature Park |  | Services | Cllr David Harris | None allocated | To be confirmed as capacity is available. | The Bid was not successful so this will be taken forward internally as capacity allows. | Weymouth has integrated walking and cycling routes.
Visitor numbers go up during the off season
Paths are promoted via leaflet/app etc
A 2 | Engage with young people to determine a project they wish to take forward, possibly a youth council |  | Services | Cllr Alex Fuhrmann | £10k committeed in earmarked reserve as a Youth Reserve | TBC post covid | On hold until restrictions allow
A 3 | Open up Tumbledown recreation area for public access and arranging learning and other projects including food production |  | Services | Cllr Jon Orrell | £100k allocated within reserves. Tumbledown operational budget has been established. | Initial work completed. | Tumbledown has been opened up, and additional projects are now in progress. | Business plan objectives met
A 4 | To move toward more community based events for local people |  | Services | Tony Hurley | No specific allocation - sits within current events budgets. | September 2021 – depending on Covid restrictions. | Agreed direction. Events Teams producing ‘menu’ of services to be offered to community groups. | KPIs in the Service Plan met (detail to be added when KPIs agreed)
A 5 | Consult to determine what community groups need and formulate a plan to deliver that support | TBC | Services | Jane Biscombe | None allocated | TBC | On hold until restrictions allow, some work via Neighbourhood Plan. | Community groups are better supported. Plan will detail agreed outcomes
A 6 | Determine how the Council can best support its residents who are experiencing poor social mobility and have poor economic prospects | TBC | Services | Jane Biscombe | None allocated | TBC | On hold until capacity is available
A7 | Mural Trail | TBC | Services | Tony Hurley | £25,000 in budget, awaiting confirmation of funding from the BID | TBC | Call for artists issued. | The mural trail is installed and becomes a loved attraction.

## B Greener & Cleaner in Activity
B - Work to Become Greener and Cleaner in our Activities as well as Supporting our Communities and Partners to be as Green as Possible
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding allocated | Timescale | Comments | What success looks like
B1 | Assess all aspects of WTC’s activities and seek ways to reduce its carbon usage to zero by 2030 | In accordance with mitigation Action Plan | Services | Charmaine Denny | None at this stage | 2030-12-01 | Oversight via Clean & Green Working Group. | Zero Carbon emissions from Council activities by December 2030
Action plan approved at 24-02-21 Full Council
B2 | Work with Dorset Council to review the recycling rates and waste collection arrangements on the beach and promenade areas |  | Services | Tony Hurley | None at this stage | 2021-09-01 | Member working group established to review the requirements for a new waste contract.
B3 | Explore the feasibility of providing charging points on Council owned land adjacent to Dorset Council owned car parks |  | Finance and Governance | Tony Hurley | None at this stage | 2022-04-01
B4 | Draw up a business plan to replace WTC’s vehicle and machinery fleet with electric (or hydrogen fuelled if available) |  | Services | Tony Hurley / Tara Williams | None at this stage | 2022-04-01

## C Promote Economic Success
C - Promote Opportunities for the Economic Success of the Area
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding Allocated | Timescale | Comments | What success looks like
C1 | Promote and develop tourism opportunities based upon Council land and assets | TBC | Services | Charmaine Denny | None at this stage | On-Going | Officers continue to investigate and progress opportunities agreed through PID process
C2 | Look into letting out WTC buildings and land for other uses such as wedding venues etc |  | Finance and Governance | Tony Hurley | None at this stage | 2021-09-01 | Progress depending on Covid restrictions.

## D Manage Assets & Resources
D - Manage the Council’s Assets and Resources Responsibly and Transparently
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding Allocated | Timescale | Comments | What success looks like
D1 | Draw up a list of potential spaces to be left as green spaces or used for tree planting, solar panels / farms, relaxation spaces, wildflower areas etc | TBA | Services | Tara Williams | None at this stage | 2022-01-01 | Form’s part of the Full Assets Review and resulting activities; and Parks & Open Spaces Strategy | Actions realised
D2 | To consider solar panels on Council buildings as part of WTC’s drive to reduce its carbon usage to zero by 2030 |  | Finance and Governance | Charmaine Denny | None at this stage | 2021/22 Financial Year | PID agreed - February 2021 Finance & Governance Committee | Estimated benefits - 6 identified sites
Annual Energy Savings = £4,889
Annual Energy Savings = KWh 32,619
Simple payback years = 6.7 yrs
Carbon Impact (Year 1) = 9.1 tCO2e
D3 | Review the Council’s assets and identify opportunities for generating increased financial returns |  | Finance and Governance | Charmaine Denny | None at this stage | 2021-10-01 | Form’s part of the Full Assets Review and resulting activities | Increased financial return to support Council Services
D4 | Set up the two catering provisions on the seafront as part of the commercialisation work |  | Finance and Governance | Charmaine Denny | £85.5k allocated from reserves to fund setup costs. An operation budget has been established. | By May 2021 | In progress – new Prom Café and new Beach Café at Greenhill
D5 | Open up the Commercial Road offices to wedding ceremonies as part of the commercialisation work |  | Finance and Governance | Tony Hurley | None at this stage | By May 2021 | Practical arrangements being made with Dorset Council
D6 | Consider moving the nursery to Tumbledown to reduce costs |  | Services | Tara Williams/Charmaine Denny | None at this stage | 2022-01-01 | Final Nursery relocation plan to be presented to the October Services Committee, alongside Parks & Open Spaces Strategy - these documents will progress to the Finance & Governance Committee (December 2021) and onto Full Council (January 2022) for decision. | Efficient Nursey Provision that meets Councils and Communities requirements

## E Manage services Effectively
E - Manage the Council’s Services Effectively to Meet the Needs of the Community we Serve
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding Allocated | Timescale | Comments | What success looks like
E1 | Assess and consider providing more services via directly employed staff rather than contracting out |  | HR / Finance and Governance | Tony Hurley | None at this stage |  | Toilet cleansing now in house. New Catering service is in-house.
E2 | Work with Dorset Council to review the number and quality of the waste bins available on the beach and promenade areas |  | Finance and Governance | Tony Hurley | None at this stage | 2021-09-01
E3 | Agree a Community Emergency Plan |  | Finance and Governance | Ian Milne | None required | By May 2021 | Committee to determine May 2021 | Emergency Plan and response that can be enacted in support of our Community
E4 | Provide a full Bereavement Services function for burials and memorials within Weymouth Cemeteries |  | Services | Tara Williams | None at this stage | 2021-03-01 | In progress

## F Strive for continuous dvlpmnt
F - Strive for Continuous Improvement and Service Development
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Fundng Allocated | Timescale | Comments | What success looks like
F1 | Draw up a 4 year plan to transform WTC’s parks, gardens and open spaces |  | Services | Tara Williams | TBC | Autumn 2021 | In progress
F2 | Produce a Parks and Open Spaces biodiversity plan, including site specific action plans |  | Services | Tara Williams | None required | 2021-12-01 | In progress
F3 | Deliver the Radipole Park and Gardens Heritage Lottery Fund project | As detailed in the detailed project plan | Services | Jane Biscombe | Heritage lottery funding of £1.013m. S106 funds also held to allocate against this project. | Mid 2023 | Stage 2 commenced Jan 2021 | The plan is delivered as agreed, and user satisfaction is high.
F4 | Complete the Marsh Masterplan improvement work |  | Services | Tara Williams | Section 106 funding | 2021-11-01 | In progress
F5 | Develop a nature trail and wildflower area at Greenhill |  | Services | Tara Williams |  | 2021-04-01 | In progress
F6 | Review the staff base to ensure new areas of work are properly resourced | Report to HR in spring | HR | Jane Biscombe | As per HR Committee agreement | Autumn 2021 | In progress | The Council has a staff team with capacity and skills to meet the needs of the Council and identified priorities.
Agreed in Nov 21 for inclusion in budget proposals.
F7 | Tender for our IT provision to ensure best value |  | Finance and Governance | Ian Milne | None at this stage | Autumn 2021
F8 | Put in place an out of hours provision to ensure effective emergency management |  | Finance and Governance | Charmaine Denny | None at this stage | Autumn 2021 | In progress
F9 | Develop a tree trail at Lodmoor Country Park |  | Services | Tara Williams | TBC | 2021-07-01 | In progress

## G Work with partners
G - Work with Partners to Deliver our Core Values and Strategy
Action | Action Detail | Milestones | Council Committee | Lead Member / SMT Officer | Funding Allocated | Timescale | Comments | What success looks like
G1 | Work with community partners to draft a neighbourhood Plan for Weymouth |  | Planning and Licensing / Finance and Governance | Cllr Lucy Hamilton / Cllr David Northam | £70,300 allocated from CIL | By end 2023
G2 | To work with Dorset Council to evaluate the possibility, and consult on, long term plans for both sides of the harbour area | Briefing held in March 21 | TBC | Jane Biscombe | None at this stage | TBC | In progress. | Long term plans agreed with DC
Long term plans successfully implemented
G3 | Work with Dorset Council to agree a Boundary Review | Proposal from Governance group | Finance and Governance | Cllr David Harris / Cllr Luke Wakeling | None required | By end 2021 | In progress | Review in place for elections in 2024
Agreement by Full Council
Submission to DC
G4 | Work with Police and DC to agree how the Council can best contribute to addressing anti-social behaviour | CSAS SLA agreed | Finance and Governance | Jane Biscombe | None at this stage | 2021-03-01 | SLA in progress | There are effective ways in place to direct activity to areas identified by the Council
Wider discussion required
G5 | Work with partners to develop affordable housing for local residents |  | TBC | TBC | None at this stage | TBC | Link to Local Plan and Neighbourhood Plan